### Goals Contract for MET 431 / 531

This Agreement is entered into on February 2nd, 2026, between all members of the group working with Everstream Analytics and the advisor for this course, herein referred to as “Parties”. Any breach of this agreement may result in grade-based penalties.

### Section 1: Goals

The Parties agree to work collaboratively and with our private sector partner to achieve the following overall goals with respect to problems raised by Everstream Analytics:

- Create a problem statement and project description.

  - Describe the hazards to partners from anomalously high/low temperature and precipitation.

  - Summarize the current problems with long-term forecasting and how teleconnections can be used to help.

  - Create a potential methodology for using teleconnection patterns to help drive long-term forecasts.

- Design a feasible, cost-effective project to address the problem

  - Obtain and pre-process teleconnection, regional temperature, and precipitation data provided by Everstream.

  - Discuss with team on specific approaches and strategies for analyzing the data.

- Deliver the completed project to Everstream Analytics

  - Create a statistical analysis of each relevant teleconnection pattern and how each pattern correlates to above or below average temperature/precipitation.

  - Generate a set of Jupyter Notebooks and/or scripts to take this analysis and turn it into a functional product to be built upon by Everstream (Optionally, if time permits, experiment with using a ML approach for this product).

  - All relevant materials, including reports, presentations, code, documentation, etc. Will be compiled and archived into a folder to be shared with Everstream at the conclusion of the project.

The Parties agree to work collaboratively and with our private sector partner to achieve these secondary goals that support achieving the overall goals:

- Communicate with Everstream Analytics contact(s)

  - Maintain regular and continuous contact with our primary Everstream contact Logan Bundy.

- Professionally present your progress to Everstream Analytics contact(s) on or around March 2nd, 2026.

  - Data will be gathered and provided to the team by Logan.

  - Data will be analyzed by Owen and Matthew, with guidance from Tyson and Landon.

  - Preliminary analysis and correlation results will be used to build the model.

- Professionally present your completed work to Everstream Analytics contact(s) on or around April 27th, 2026.

  - Finalized analysis and correlation results will be presented based on revisions from the midterm report.

  - A report on teleconnection correlation in each region will be provided.

  - Example output tables will be shown.

  - A framework for the model, including potential insights for an ML approach, will be given.

The Parties agree to work collaboratively and with our private sector partner to develop the following products that support achieving the secondary and overall goals:

- An annotated bibliography that summarizes relevant, prior research on the subject matter

  - Sources to be utilized will be cataloged and archived in a shared document, available to all team members.

  - May be merged into the mid-semester report as necessary.

- A word document cataloging and describing pertinent visualizations

  - Will contain any/all figures generated throughout the project.

  - May be created as an addendum to the mid-semester/final report.

- All code created to generate, analyze and/or visualize the data and product framework

  - Code will be in the form of Jupyter Notebooks and scripts that will be stored in a shared folder.

  - Any/all data used in the created code will either be stored and organized within the share folder or clearly documented as to how to obtain said data.

  - All code will be created with documentation and best practices in mind so that future work can easily be done.

- A mid-semester report and associated oral presentation

  - The report will be built by the whole team, with individual journals serving as supporting documentation of progress.

  - The main data analyzers will report on findings of teleconnection correlations.

  - The methods/model-builders will report on initial design of models and plans for the following month.

- An end of semester report and associated oral presentation

  - Final report will start being written after mid-term report, which will serve as a foundation for the final report.

  - Sections will be divided up based on prior tasks throughout the semester to individuals, respectively.

  - Presentation will be broken up evenly.

- Weekly journal sets of individual and team-based progress documentation

  - Individual team members will record both individual and team progress in their journals.

  - Progress will be based off individual efforts, task completion, and shared document contribution.

- Semi-monthly group evaluations

  - Group members will be evaluated on an individual basis from contribution and discussion participation.

  - Evaluations will also contain feedback on group dynamic and highlight any issues.

- Peer-review and feedback of progress of other group during report presentations

  - Group will provide written feedback and constructive criticism on methods and progress and provide ideas on how to improve to the other group.

Section 2: Ethics and Standards

The Parties agree to work collaboratively and with our private sector partner in an ethical way that includes the following guiding principles (https://www.acm.org/code-of-ethics):

- Contribute to society and to human well-being.

- Avoid creating physical and mental harm.

- Be honest and trustworthy by using transparent methods and never creating fake data or analysis.

- Be fair and take action not to discriminate by avoiding biases and remaining objectives.

- Respect existing work used by this project through acknowledgements and citations.

- Respect privacy if personal information is used in this work.

- Honor confidentiality by not discussing this work with others.

- Maintain high standards and produce the highest quality of work based on your experience. Do not be afraid to speak up if you are not familiar with a topic assigned to you.

- Be professional when critiquing the work of others. For serious issues, one-on-one conversations are better than public admonishment.

- Use existing computing resources responsibly by approaching code execution only after you have a well-developed plan.

After you complete this document, you should bring it to your instructor. If no changes are needed, each member should sign below by typing their name and the date to acknowledge they have read the Goals Contract and understand what is expected of them during the course:

| Member Signature | Date |
| --- | --- |
| Matthew Woods | 2/4/26 |
| Tyson Stewart | 2/4/26 |
| Owen Cutinello | 2/4/26 |
| Landon Moeller | 2/4/26 |